## Current Meeting
Minutes Of Meeting for the call AR Team held on 19th Mar'19
Participants | Ramesh Sethuraman, Santha Kumar, Paul Robert, Georgi, Mahesh, Sarah Walker,Peter Weir, Chris Lodge, Anne Markland,Simon Johnson,Brendan Welsh
Excuses | Richard Cottam,
Action Log
Sr.No | Topic Discussed | Action To be | Owner | Target Date | Current Status
1 | Call Drop | Unanswered call rate is very high- 16%. Reason and mitigation plan is required to bring down below 10% Sofia team to check the call report Daily/weekly, any discrepancy found needs to raise with service desk | Georgi | 26th Mar'19 | Open
2 | Collections Slide | Collections Query value to show exact number | Paul | 26th Mar'19 | Closed
3 | PP Customer | Call to schedule with Sofia team, Sheffield team & Cash apps to understand the PP customer portal and see how it works | Paul | 29th Mar'19 | Open
4 | Unallocated | Unallocated – 60+ days payments to be worked and clear the payments ¦ Reach out to collectors for support | Paul | 29th Mar'19 | Open
5 | Remits | All remits should go smart AR | Paul | 26th Mar'19 | Closed
6 | Bank statement Posting | There is dependence from Sheffield team to post Chaps Payment in K8. BACs payments will be posted before 8 AM BST | Paul | 26th Mar'19 | Closed
7 | Bank statement Posting | Chaps with the help of Sheffield team posted before 8:30 AM | Paul | 29th Mar'19 | Open
8 | Credit Services | Simon will be sending the non-compliance report for credit, TAT needs to be checked, also if any authorization issue needs to be highlighted | Simon | 26th Mar'19 | Open
9 | Under & Over banking | To see if we schedule a session with Vignesh for the team member, also to work with GA team | Paul | 29th Mar'19 | Open
10 | Issue Log | Bad debts analysis to check and update | Paul | 26th Mar'19 | Open
11 | MIS Reporting | MIS reporting needs to checked, Ramesh to sit with MIS team | Ramesh | 29th Mar'19 | Closed
12 | CAPA | Error file to check and close with Sofia team | Paul | 26th Mar'19 | Closed