## 12 Mar
Minutes Of Meeting for the call AR Team held on 12th Mar'19
Participants | Ramesh Sethuraman, Santha Kumar, Paul Robert, Georgi, Mahesh, Sarah Walker,Peter Weir, Chris Lodge, Anne Markland
Excuses | Simon Johnson, Richard Cottam, Brendan Welsh
Action Log
Sr.No | Topic Discussed | Action To be | Owner | Target Date | Current Status
1 | Share Drive Issue | Call to schedule for pending & Shared drive issue, that should reduce time to post cash | Ciaran | 13th Mar'19 | Open
2 | Collection Over due | SIG E & D overdue & Month 4+ ¦ Count and Value have the same numbers | Paul | 19th Mar'19 | Closed
3 | Call Drops (Missed Calls) - Collections | Shantha to check on 40% drop calls review & update action in the next call | Santha | 19th Mar'19 | Closed
4 | SIG E Traget - Cash flow | SIGE target seems to be high Anne/Georgi to check were it is coming from¦ this has been corrected - Paul | Anne/Georgi | 19th Mar'19 | Closed
5 | CHQ Batch Issue | Sarah to send an email summarizing chq batch issue to Siman for resolutions & to add it to the log | Anne/Georgi | 11th Mar'19 | Open
6 | Cash App - Postings | To test if we can post the payments by 10AM IST to improve the order release | Paul | 19th Mar'19 | Closed
7 | Issue Log | Issue log to be updated and share the same with Simon | Paul | 19th Mar'19 | Closed

## 19 Mar
Minutes Of Meeting for the call AR Team held on 19th Mar'19
Participants | Ramesh Sethuraman, Santha Kumar, Paul Robert, Georgi, Mahesh, Sarah Walker,Peter Weir, Chris Lodge, Anne Markland,Simon Johnson,
Excuses | Richard Cottam, Brendan Welsh
Action Log
Sr.No | Topic Discussed | Action To be | Owner | Target Date | Current Status
1 | Call Drop | Unanswered call rate is very high- 16%. Reason and mitigation plan is required to bring down below 10% Sofia team to check the call report Daily/weekly, any discrepancy found needs to raise with service desk | Georgi | 26th Mar'19 | Closed
2 | Collections Slide | Collections Query value to show exact number | Paul | 26th Mar'19 | Closed
3 | PP Customer | Call to schedule with Sofia team, Sheffield team & Cash apps to understand the PP customer portal and see how it works | Paul | 29th Mar'19 | WIP
4 | Unallocated | Unallocated – 60+ days payments to be worked and clear the payments ¦ Reach out to collectors for support | Paul | 29th Mar'19 | WIP
5 | Remits | All remits should go smart AR | Paul | 26th Mar'19 | Closed
6 | Bank statement Posting | There is dependence from Sheffield team to post Chaps Payment in K8. BACs payments will be posted before 8 AM BST | Paul | 26th Mar'19 | Closed
7 | Bank statement Posting | Chaps with the help of Sheffield team posted before 8:30 AM | Paul | 29th Mar'19 | Closed
8 | Credit Services | Simon will be sending the non-compliance report for credit, TAT needs to be checked, also if any authorization issue needs to be highlighted | Simon | 26th Mar'19 | Open
9 | Under & Over banking | To see if we schedule a session with Vignesh for the team member, also to work with GA team | Paul | 29th Mar'19 | WIP
10 | Issue Log | Bad debts analysis to be checked and update | Paul | 26th Mar'19 | Open
11 | MIS Reporting | MIS reporting needs to checked, Ramesh to sit with MIS team | Ramesh | 29th Mar'19 | Closed
12 | CAPA | Error file to check and close with Sofia team | Paul | 26th Mar'19 | Closed

## 26 Mar
Minutes Of Meeting for the call AR Team held on 26th Mar'19
Participants | Ramesh Sethuraman,Georgi, Mahesh,Simon Johnson,Richard Cottam, Anne Markland,Paul Robert
Excuses | Peter Weir,
Action Log
Sr.No | Topic Discussed | Action To be | Owner | Target Date | Current Status
1 | Call Drop | To share revised Unanswered % ¦ Need to bring down Unanswered call % | Georgi | 2nd Apr'19 | Open
2 | Call Volume | Outgoing call volume to be improved as the overdue account numbers do not match with the call count | Georgi | 2nd Apr'19 | Closed
3 | Collections Resources | Additional Resources to hire by End of April'19 | Georgi | 1st May'19 | Open
4 | Collection Query | Query details to be checked, especially top accounts | Georgi | 2nd Apr'19 | Open
5 | Error Log | To share the Error Log based on audits starting next week | Paul/Georgi | 2nd Apr'19 | Closed
6 | Credit | Simon appreciated Credit team for the TAT maintained around 1.5 | - |  | Closed
7 | House keeping report | Revised template will be shared by Simon once Sarah is back from holidays | Simon/Paul | 2nd Apr'19 | Open
8 | Cardnet | Cardnet status update and plan to bring down the recon to be shared with Simon | Paul | 29th Mar'19 | WIP
9 | Under & Over Banking | Ramesh Raised concerns & Issues faced with Branches for non responsiveness¦ Simon to address this with Branch | Simon |  | Open
10 | CA Error log | Paul has shared the error log with RCA and CAPA for the issues highlighted by SIG the previous week¦ 3 errors out of 8 were done by CA | Paul | 2019-03-26 | Closed
11 | Unanswered Call Report correction Status | Call Unanswered reports were corrected by IT team ¦No further action is required | Paul | 2019-03-26 | Closed
12 | unable to view PODs in K8(Sofia and Chennai) | Raise a new Ticket | Paul | 2019-04-02 | Open

## 2 Apr
Minutes Of Meeting for the call AR Team held on 2nd Apr'19
Participants | Simon Johnson,Richard Cottam, Anne Markland,Ramesh Sethuraman,Georgi, Mahesh,Paul Robert,Kiran,Santha
Excuses | Peter Weir,
Action Log
Sr.No | Topic Discussed | Action To be | Action Taken | Owner | Target Date | Current Status
1 | Missed Calls | To check and advise the call drop & provide the action plan, also to check if the call lands before shift hrs |  | Georgi | 2019-04-09 | WIP
2 | Query | SIG D Query Value to be checked and update, 1.8M which is Low compared with SIG E |  | Ramesh | 2019-04-09 | WIP
3 | Credit Service | Rejection reason to be shared to see if any improvement. |  | Mahesh/Paul | 2019-04-08 | WIP
4 | Cash Apps | To check if SGS team can move CHAPS file and post the payments in K8 directly, to avoid dependence from Sheffield team. | Tested from MI team system, same error,team wasn't able to move Chaps file. | Ramesh /Paul | 2019-04-03 | Closed
5 | Collections | Early Login Plan, Georgi had highlighted that branches starts calling the team from 6:30 AM¦Due to increased call volume, the call are dropped. |  | Georgi | 2019-04-03 | Closed
6 | Error log | Question on what basis CA errors are captured, Ramesh explained that only the external errors higlighted to Leads are tracked and published. Error log to be updated and placed in share drive so that everyone has the visibility of it (Share the Link) and the same will be shared to all at the end of every week. Credit Error also to be included | Error Log is Placed in the share drive¦will communicate the same to Simon | Paul/Mahesh | 2019-04-08 | WIP
7 | Issue Log | Simon will review and confirm the list of Issues can be closed from the list shared¦ Ciaran is working on fixing POD issues for Sofia Team |  | Simon | 2019-04-09 | WIP
8 | Unallocated Report | 7.8m WIP Unallocated Cash¦ Good Imrpovement ¦60+ days analysis to be shared to Simon. |  | Paul/Mahesh | 2019-04-08 | WIP
9 | PP account - Access & training | Request access to Credit collector & later to schedule the training on how to check and allocate the payment. Also to see if we can get the full order data from K8. Georgi to check and come back on the same |  | Paul/Georgi | 2019-04-09 | WIP
10 | Cardnet | Action Plan on Cardnet progress¦current payments to be worked on as well along with backlog |  | Paul/Mahesh | 2019-04-05 | Open
11 | Under & Over banking | Vignesh & Gowtham to work together and complete the process map. Team to concentrate on high values. Action Plans to be shared |  | GA/AR | 2019-04-05 | Open
12 | Collections - Replacement | 2 HC -Backfill status was discussed | Hiring in Progress | Gerogi |  | WIP

## 9th Apr
Minutes Of Meeting for the call AR Team held on 2nd Apr'19
Participants | Simon Johnson,Richard Cottam, Anne Markland,Ramesh Sethuraman,Georgi, Mahesh,Paul Robert,Kiran,Santha
Excuses | Peter Weir,
Action Log
Sr.No | Topic Discussed | Action To be | Action Taken | Owner | Target Date | Current Status
1 | Missed Calls | Georgi to work with Steve and analysis the call report as to when the call volume flow is high. Also 3 collector logining early |  | Georgi | 2019-04-16
2 | Query | To check 4+ month data seems to be incorrect in SIG D |  | Ramesh | 2019-04-16
3 | Credit Service | Dorman account details to share with Simon | Shared with Simon | Mahesh/Paul | 2019-04-10 | Closed
4 | Cash Apps | Suspense account report to share with all on regular basis, Unallocated report to share on daily basis. | Started sharing the files | Ramesh /Paul | 2019-04-10 | Closed
5 | Error log | Question raised on number error, however sara higlighted that the error were not made by team. due to Auto Post the payment sitting in incorrect account. |  | Paul/Mahesh | 2019-04-10 | Closed
6 | Unallocated Report | Unallocated report to share on daily basis, also need to work on 90+ items with the detailed comments and share the same to Simon. |  | Paul/Mahesh | 2019-04-16 | WIP
7 | PP account - Access & training | Request access to Credit collector & later to schedule the training on how to check and allocate the payment. Also to see if we can get the full order data from K8. Georgi to check and come back on the same |  | Paul/Georgi | 2019-04-16 | WIP
8 | Cardnet | Historical analysis on Cardnet is been requested by Simon, also requested Simon to provide escalation matrix for De-falter in closing the till from branch side |  | Paul/Mahesh | 2019-04-16 | Open
9 | Collections - Replacement | 2 HC -Backfill status was discussed | Hiring in Progress | Gerogi | 2019-05-01 | WIP
10 | OCR Automation | ORC progress to update on regular basis |  | Ramesh | 2019-04-16 | WIP
11 | Slides | To check and validate the slides before sharing it to All |  | Paul/Mahesh | 2019-04-16 | WIP